## Risk Register
Risk Identification | [6 empty] | Qualitative |  |  | Quantitively |  |  | Responses and Control
# | Description | Date Identified | Last Update | Category | Trigger | Threat / Opportunity (T/O) | Probability(1-5) | Impact (1-5) | Risk Rating | Probability (%) | Cost $M | Schedule (wk days) | Risk Owner | Response Strategy | Response | Response Owner | Status | Response Notes
3.1 | Quality and timeleness of user management module may not be adaquate causing a delay to the planned release of v1 of the project. Quality of contracted user management module needs to be bug free and on time. There is some concern that the vendor will be able to meet the requirements on schedule. | 2017-01-15 | 2017-02-10 | Exteral - Subcontractors | Contracted inspection date for contracted software indicates poor progress or quality. Schedule date is March 15, 2017. | T | 2 | 3 | 6 | 25 | 10 | 3 | Mike Jones | Mitigate | If issue triggers a COTS, but less featured system will be installed for v1 release. Vendor of custom solution module will be used on v2. | Mike Jones | Active
2.1 | A new reporting tool is panned for release for a March 30th which will allow a reduction of 4 weeks of development to be reduced for reporting featers on v1 release. New reporting tool may allow for more comprehensive user activity reporting if the version ships in time to be incorporated into v1 release. It is anticipated that the new tool will significantly reduce development time and cost of reporting module. | 2016-12-29 | 2017-02-05 | Technical - Requirements | New reporting tool launch before stakeholder demo #1 on March 30, 2017. | O | 4 | 4 | 16 | 75 | -30 | 4 | Mary Smith | Enhance | Development team indicates that if new reporting tool is available and stable by stakeholder demo #1 it will be able to be incorporated into the v1 release with little risk. Publisher indicates that beta will be ready by the beginning of March with a ship date three weeks later. They have a good reputation for meeting their dates. To enhance the opportunity the development and testing team will evaluate and participate in the beta program. | Jose Camacho | Active

## Validation
Risk Type | T | O | Status | Categories | External - Subcontractors
T | Avoid | Exploit | Active |  | External
O | Transfer | Enhance | Occurred |  | External - Market
| Mitigate | Share | Complete |  | Organizational
| Accept | Accept | Watch |  | Organizational - Budget
|  |  | Retired |  | Organizational - Executive Support
Organizational - Staff
Project Management
Project Management - Estimating
Project Management - Risk Management
Stakeholders - Legal
Stakeholders - Public Relations
Technical
Technical - Performance
Technical - Quality
Technical - Requirements